CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Hanoi, September 2026 –

Table of Contents

Change Log	3

I. Project Overview	3

1. Scope and Purpose	3

2. Assumptions and Constraints	4

3. Cost and Time Estimations	5

4. Capacity Planning	7

5. Project Objectives	8

6. Risks and Mitigations	9

II. Management Approach	9

1. Project Process and Methodology	9

AI-DLC Inception	10

AI-DLC Construction	10

AI-DLC Build and Test	10

Integration Gates	10

2. Quality Management	11

Requirements and Design Quality	11

Code Quality	11

Testing Quality	11

AI Quality and Governance	11

Definition of Done	12

3. Project Training Plan	12

4. Responsibility Assignments	12

Project Organization	12

RACI Chart	13

5. Project Communications	15

6. Configuration Management	16

6.1 Document Management	16

6.2 Source Code Management	16

6.3 Tools and Infrastructures	17

# Change Log

| Date | A/M/D | In Charge | Change Description |
| --- | --- | --- | --- |
| 14/09/2026 | A | Khuất Quang Hưng | Created Project Management Plan v1.0 |

A - Added, M - Modified, D - Deleted

# I. Project Overview

## 1. Scope and Purpose

AI-Powered Comprehensive Learning Platform, abbreviated as APLP, is a desktop-first responsive web application designed to support teaching and learning activities within a university or training institution.

The platform provides a unified environment for managing institution-issued accounts, academic subjects, classes, learning materials, assignments, individual and group submissions, grading, payments, notifications and audit records.

The system supports four main user roles: Learner, Instructor, Subject Manager and Administrator. A Subject Manager inherits Instructor capabilities within assigned subjects and classes.

The project includes the following major functions:

- Institution-issued account authentication and account lifecycle management.

- Role-based, scope-based and object-level authorization.

- Subject, course offering, class and enrollment management.

- Class-specific content and shared subject-level RAG repositories.

- Learning-material and progress management.

- Question bank and rubric bank management.

- Manual and AI-assisted assignment authoring.

- Assignment review, scheduling and publication.

- Essay, multiple-choice, Code Lab and UML practical assignments.

- Embedded Draw.io canvas and complete XML submission.

- Individual and group assignment workflows.

- Submission attempts and immutable submission versions.

- Manual, deterministic and AI-assisted grading.

- Payment verification and access-entitlement management.

- Notifications, reporting and audit records.

- Private file storage through organizational Google Drive.

- Temporary state in Redis and background-job processing through RabbitMQ.

The project is divided into eight AI-DLC units:

- U01 - Platform Foundation and Identity.

- U02 - Academic Administration.

- U03 - Content, Learning and Banks.

- U04 - Assessment Authoring and Publication.

- U05 - Submission and Group Work.

- U06 - Grading, AI and Code Execution.

- U07 - Reporting and Notification.

- U08 - Payment and Entitlement.

The MVP excludes native mobile applications, public self-registration, multi-organization tenancy, public file sharing, automatic publication of AI-generated content and automatic final grading by AI.

Phase 2 features such as invitation-code enrollment, class discussion, individual deadline extensions, grade appeals, similarity review and advanced analytics are excluded from the committed MVP.

## 2. Assumptions and Constraints

| No. | Description | Note |
| --- | --- | --- |
|  | Assumptions |  |
| 1 | The project team consists of five SEP490-G21 members. | Resources |
| 2 | Each member can contribute approximately 20 hours per week. | Capacity |
| 3 | The supervisor reviews major milestone documents and demonstrations. | Stakeholder |
| 4 | Report 1 and approved AI-DLC artifacts are the project baseline. | Baseline |
| 5 | Sandbox, mock or development versions of external services are available for testing. | External interfaces |
|  | Constraints |  |
| 1 | The project must be completed within 15 weeks. | Schedule |
| 2 | Effective project capacity is limited to 1,200 hours or 150 person-days. | Resources |
| 3 | The product is a desktop-first responsive web application. | Technology |
| 4 | AI-generated assignments and grading results require authorized human approval. | Quality |
| 5 | Private files must remain protected behind backend authorization. | Security |
| 6 | External-provider failures must not corrupt academic, payment or submission records. | Resiliency |

## 3. Cost and Time Estimations

| # | Work Package | Effort (pds) | Due Date |
| --- | --- | --- | --- |
| 1 | Stage 1: Project Initiating (week 1) | 4 | End of Week 1 |
| 1.1 | Report 1 (Project Introduction) | 4 | Week 1 |
| 2 | Stage 2: Project Planning & Initial Requirements (weeks 2-3) | 16 | End of Week 3 |
| 2.1 | Report 3: SRS v0.9 (Overall Requirement) | 8 | Week 2 |
| 2.2 | Vertical Prototypes (Code Demo) | 4 | Week 3 |
| 2.3 | Report 2: Project Management Plan v1.0 | 4 | Week 2 |
| 3 | Stage 3: Software Design (weeks 4-5) | 22 | End of Week 5 |
| 3.1 | Vertical Prototypes (POC, or Proof of Concepts) | 5 | Week 4 |
| 3.2 | Report 4: SDS v1.0 (High Level Design Specifications) | 8 | Week 5 |
| 3.3 | Report 5: Test Planning (ref. Report5 Test Documentation) | 4 | Week 5 |
| 3.4 | Report 3: SRS v1.0 (Detailed Requirements for Iteration 1) | 5 | Week 5 |
| 4 | Stage 4: Implementation (weeks 6-11) | 82 | End of Week 11 |
|  | (Ref: Project Tracking and WBS sheet) |  |  |
| 4.1 | Implementation Iteration 1 (weeks 6-7) | 27 | End of Week 7 |
| 4.1.1 | Report 4: Detailed Design Specifications (SDS) v1.1 | 4 | Week 6 |
| 4.1.2 | Code Package & Unit Testing Report | 13 | Week 7 |
| 4.1.3 | Report 5: Integration Test Cases | 3 | Week 7 |
| 4.1.4 | Report 5: Integration Test Report | 2 | Week 7 |
| 4.1.5 | Report 3: SRS v1.1 (Detailed Requirements for Iteration 2) | 3 | Week 7 |
| 4.1.6 | Software Package Version 1 | 2 | Week 7 |
| 4.2 | Implementation Iteration 2 (weeks 8-9) | 27 | End of Week 9 |
| 4.2.1 | Report 4: Detailed Design Specifications (SDS) v1.2 | 4 | Week 8 |
| 4.2.2 | Code Package & Unit Testing Report | 13 | Week 9 |
| 4.2.3 | Report 5: Integration Test Cases | 3 | Week 9 |
| 4.2.4 | Report 5: Integration Test Report | 2 | Week 9 |
| 4.2.5 | Report 3: SRS v1.2 (Detailed Requirements for Iteration 3) | 3 | Week 9 |
| 4.2.6 | Software Package Version 2 | 2 | Week 9 |
| 4.3 | Implementation Iteration 3 (weeks 10-11) | 28 | End of Week 11 |
| 4.3.1 | Report 4: Detailed Design Specifications (SDS) v1.3 | 4 | Week 10 |
| 4.3.2 | Code Package & Unit Testing Report | 13 | Week 11 |
| 4.3.3 | Report 5: Integration Test Cases | 3 | Week 11 |
| 4.3.4 | Report 5: Integration Test Report | 2 | Week 11 |
| 4.3.5 | Report 5: System Test Cases | 4 | Week 11 |
| 4.3.6 | Software Package Version 3 | 2 | Week 11 |
| 5 | Stage 5: Verification & Validation (weeks 12-13) | 15 | End of Week 13 |
| 5.1 | Report 5: System Test Report | 6 | Week 12 |
| 5.2 | Report 5: Acceptance Test Support | 4 | Week 13 |
| 5.3 | Report 6: User Guides (Installation Guides, User Manuals) | 3 | Week 13 |
| 5.4 | Final Software Package (Documents, Source Codes, etc.) | 2 | Week 13 |
| 6 | Stage 6: Closing (weeks 14-15) | 11 | End of Week 15 |
| 6.1 | Report 7: Final Project Report | 6 | Week 14 |
| 6.2 | Presentation File | 3 | Week 14 |
| 6.3 | Demo Rehearsal, Project Defense and Final Handover | 2 | Week 15 |
|  | Total Effective Effort | 150 pds | 15 weeks |

The work-package structure follows the university capstone template. AI-DLC is applied as the project governance and development workflow.

Stages 1 to 3 correspond to AI-DLC Inception. Stage 4 corresponds to AI-DLC Construction. Stage 5 corresponds to AI-DLC Build and Test. Stage 6 covers project closing, reporting and defense.

| Iteration | AI-DLC Units | Main Outcome |
| --- | --- | --- |
| Iteration 1 | U01 and U02 | Platform foundation, identity, authorization and academic administration |
| Iteration 2 | U03, U04 and U08 | Content, RAG, assessment authoring, publication, payment and entitlement |
| Iteration 3 | U05, U06 and U07 | Submission, group work, grading, AI, Code Lab, reporting and notifications |

## 4. Capacity Planning

| Item | Value |
| --- | --- |
| Number of team members | 5 members |
| Hours per person per week | 20 hours |
| Team capacity per week | 100 hours |
| Total duration | 15 weeks |
| Gross capacity | 1,500 hours or 187.5 person-days |
| Buffer for meetings, reviews and unplanned work | 20% |
| Reserved capacity | 300 hours or 37.5 person-days |
| Effective working capacity | 1,200 hours or 150 person-days |

One person-day is calculated as eight working hours. The 20% buffer covers meetings, reviews, AI-DLC approval checkpoints, defect investigation, integration support and unexpected external-provider problems.

The Leader and Tech Lead review actual effort against the plan every week. When a work package is forecast to exceed its estimate, the team may reassign resources, use the project buffer or postpone Phase 2 functions.

## 5. Project Objectives

| # | Metric | Unit | Planned | Actual | Notes / References |
| --- | --- | --- | --- | --- | --- |
| 1 | Effective effort usage | Person-day | <= 150 | TBD | Weekly capacity tracking |
| 2 | Requirements and design review coverage | % | 100% | TBD | AI-DLC approval gates |
| 3 | Pull-request review coverage | % | 100% | TBD | Source-code management |
| 4 | Business-rule unit-test coverage | % | >= 70% | TBD | Per-unit Definition of Done |
| 5 | Public-contract compatibility tests | % | 100% | TBD | API and job/event contracts |
| 6 | System-test pass rate | % | >= 95% | TBD | Containerized environment |
| 7 | Core end-to-end journeys passed | % | 100% | TBD | MVP release gate |
| 8 | On-time milestone deliverables | % | >= 90% | TBD | Approved WBS |
| 9 | Requirement and user-story traceability | % | 100% | TBD | Requirements to tests |
| 10 | Unresolved critical security defects | Number | 0 | TBD | Release-readiness gate |
| 11 | Unauthorized AI final decisions | Number | 0 | TBD | AI governance requirement |
| 12 | Duplicate payment or submission records | Number | 0 | TBD | Idempotency requirement |

The Actual column will be completed at project closing using test reports, project-tracking records, Git history and AI-DLC traceability evidence.

## 6. Risks and Mitigations

| # | Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R01 | MVP scope increases after the requirements baseline is approved. | Medium | High | Freeze the MVP baseline after Week 3. Every change requires impact analysis. Defer Phase 2 functions first. |
| R02 | AI, payment, notification, Google Drive or Code Sandbox services become unavailable. | Medium | High | Use adapters, sandbox or mock contracts, timeouts, bounded retries and a fallback demonstration plan. |
| R03 | Async jobs, file handling or integration contracts produce difficult defects. | Medium | High | Version contracts, use idempotency and correlation IDs, and test with real file fixtures before closing each integration gate. |
| R04 | Member availability falls below 20 hours per week. | Medium | High | Track weekly capacity, preserve the 20% buffer, redistribute work and reduce non-MVP scope. |
| R05 | Authorization or private-file handling exposes data or blocks core workflows. | Low | High | Apply deny-by-default authorization, negative security tests, audit events and a security review before release. |

# II. Management Approach

## 1. Project Process and Methodology

The project follows an iterative and incremental methodology governed by AI-DLC.

The overall process is:

Project Initiation -> AI-DLC Inception -> Software Design -> Implementation Iterations -> Build and Test -> Project Closing

### AI-DLC Inception

AI-DLC Inception determines what the team will build and why. It includes:

- Workspace detection.

- Requirements analysis.

- Personas and user stories.

- Use cases and business flows.

- Workflow planning.

- Application and database design.

- Unit-of-work generation.

- Dependency and integration-gate planning.

Requirements and designs must be reviewed before implementation begins.

### AI-DLC Construction

Each implementation unit follows the applicable AI-DLC stages:

Functional Design -> NFR Requirements -> NFR Design -> Infrastructure Design -> Code Generation

Each stage has an approval checkpoint. The team cannot move to the next stage until the current deliverables have been reviewed.

The implementation dependency sequence is:

U01 -> U02 -> U03 and U08 -> U04 -> U05 -> U06 -> U07

U03 and U08 may be implemented in parallel after the foundation and academic contracts are stable.

### AI-DLC Build and Test

After all units are integrated, the team performs:

- Full project build.

- Unit testing.

- Integration testing.

- Contract testing.

- System testing.

- End-to-end testing.

- Security testing.

- Resiliency testing.

- Acceptance-test support.

- Release and deployment verification.

### Integration Gates

| Gate | Required Result |
| --- | --- |
| G0 - Foundation | Authentication, authorization, artifact, job and audit contracts operate correctly. |
| G1 - Academic | Subject, class and enrollment scopes are enforced server-side. |
| G2 - Content and Payment | Content access, RAG jobs and payment-entitlement contracts are compatible and idempotent. |
| G3 - Assessment | Assignment drafting, review and publication follow the correct role and scope. |
| G4 - Submission | Submission versions are immutable and only the leader submits the common group assignment. |
| G5 - Grading and AI | AI creates proposals only, educators control final grades and code runs in a restricted sandbox. |
| G6 - Reporting | Reports respect authorization and notification failures do not roll back academic transactions. |

## 2. Quality Management

Quality is managed throughout the project rather than only at the final testing stage.

### Requirements and Design Quality

- Requirements must be clear, testable and traceable.

- User stories must include acceptance criteria.

- The BA verifies consistency among requirements, user stories and use cases.

- The Tech Lead reviews architecture, component boundaries and public contracts.

- The Tester reviews whether requirements can be verified.

- The UI/UX member reviews user flows and usability requirements.

- AI-DLC documents must be updated when approved decisions change.

### Code Quality

- Development work must be linked to an issue or approved work item.

- Code must follow the architecture approved by the Tech Lead.

- Pull requests require review before merge.

- Automated checks must pass before code enters the main branch.

- Modules must communicate through approved interfaces.

- Secrets and credentials must not be committed.

- Database migrations and contract changes must be reviewed for compatibility.

### Testing Quality

The testing strategy includes:

- Unit tests for business rules and state transitions.

- Integration tests for PostgreSQL, Redis, RabbitMQ and Google Drive.

- Contract tests for APIs and background-job schemas.

- Negative tests for role, scope and object authorization.

- System tests for the complete containerized application.

- End-to-end tests for core learner and educator journeys.

- Regression tests after defect fixes.

- Acceptance tests based on approved requirements.

### AI Quality and Governance

- AI output is treated as a proposal.

- AI-generated assignments require educator review.

- AI-generated grades require educator review and finalization.

- AI cannot automatically publish assignments.

- AI cannot automatically finalize grades.

- Common group assignments are graded manually.

- AI usage and significant decisions must be auditable.

### Definition of Done

A work package is complete only when:

- Approved requirements are satisfied.

- Required design documentation is updated.

- Code has been reviewed.

- Required automated tests pass.

- Authorization and error-handling checks pass.

- No critical defect remains unresolved.

- AI-DLC checklists and approval records are updated.

## 3. Project Training Plan

| Training Area | Participants | When and Duration |
| --- | --- | --- |
| AI-DLC workflow, approval gates and traceability | All members | Week 1, 4 hours |
| Project planning and team coordination | Khuất Quang Hưng, Võ Chiến Thắng | Week 1, 4 hours |
| Requirements, use cases and acceptance criteria | Đào Chí Cường, Vũ Hải Nam | Week 1, 4 hours |
| UI/UX, user flows and responsive design | Võ Minh Tài, Đào Chí Cường | Weeks 1-2, 6 hours |
| Next.js, Spring Boot and system architecture | Võ Chiến Thắng and development participants | Weeks 1-2, 8 hours |
| PostgreSQL, Redis and RabbitMQ | Võ Chiến Thắng and development participants | Week 3, 6 hours |
| Automated testing and defect management | Vũ Hải Nam and development participants | Week 4, 6 hours |
| Security and authorization testing | Võ Chiến Thắng, Vũ Hải Nam | Week 4, 4 hours |
| Google Drive and external-service integration | Võ Chiến Thắng and relevant members | Week 6, 6 hours |
| UAT, demonstration and defense preparation | All members | Weeks 13-15, 6 hours |

Training effectiveness is evaluated through technical demonstrations, reviewed artifacts, test execution or successful completion of related work packages.

## 4. Responsibility Assignments

### Project Organization

| Full Name | Project Role | Main Responsibility |
| --- | --- | --- |
| Nguyễn Trung Kiên | Supervisor | Reviews project direction, milestone reports and final deliverables. |
| Khuất Quang Hưng | Leader | Manages scope, schedule, resources, AI-DLC checkpoints, stakeholder communication and final delivery. |
| Võ Chiến Thắng | Tech Lead | Leads architecture and technical implementation, assigns development work, reviews code and handles integration problems. |
| Đào Chí Cường | Business Analyst | Analyzes requirements, maintains the SRS, user stories, use cases and requirement traceability, and supports UAT. |
| Vũ Hải Nam | Tester | Creates test plans and test cases, performs testing, manages defects and verifies fixes. |
| Võ Minh Tài | UI/UX Designer | Designs user flows, wireframes, prototypes, UI specifications and interface consistency. |

All members may participate in implementation, documentation, reviews and demonstrations when required. The assigned role identifies each member’s primary responsibility.

### RACI Chart

R = Responsible, A = Accountable, C = Consulted, I = Informed.

| Work Package | Khuất Quang Hưng | Võ Chiến Thắng | Đào Chí Cường | Vũ Hải Nam | Võ Minh Tài |
| --- | --- | --- | --- | --- | --- |
| Project initiation and Report 1 | A/R | C | R | I | C |
| Project Management Plan | A/R | C | C | I | I |
| Requirements analysis and SRS | A | C | R | C | C |
| User stories, use cases and business flows | A | C | R | C | C |
| UI/UX design and vertical prototype | A | C | C | C | R |
| System architecture and SDS | C | A/R | C | C | C |
| Database and API design | C | A/R | C | C | I |
| U01 Platform Foundation and Identity | C | A/R | C | C | I |
| U02 Academic Administration | C | A/R | R | C | C |
| U03 Content, Learning and Banks | C | A/R | C | C | R |
| U04 Assessment Authoring and Publication | C | A/R | R | C | R |
| U05 Submission and Group Work | C | A/R | C | C | R |
| U06 Grading, AI and Code Execution | C | A/R | C | C | I |
| U07 Reporting and Notification | C | A/R | C | R | C |
| U08 Payment and Entitlement | C | A/R | C | C | R |
| Frontend implementation and UI review | C | A | C | C | R |
| Backend and worker implementation | C | A/R | C | C | I |
| Integration and contract testing | I | A | C | R | C |
| System and end-to-end testing | C | C | C | A/R | C |
| User acceptance testing | A | C | R | R | C |
| Defect and regression management | C | C | C | A/R | I |
| AI-DLC documentation and traceability | A | C | R | C | I |
| Deployment and final package | A | R | C | R | I |
| User guides and final documentation | A | C | R | C | R |
| Presentation and demonstration | A/R | R | R | R | R |
| Project defense and handover | A/R | R | R | R | R |

## 5. Project Communications

| Communication Item | Who / Target | Purpose | Frequency | Type, Tool and Method |
| --- | --- | --- | --- | --- |
| Daily stand-up | All members | Report progress, current work and blockers | Daily, 15 minutes | Online meeting or group chat |
| Weekly planning meeting | All members | Review WBS, capacity and weekly commitments | Weekly, 60 minutes | Google Meet and project board |
| Technical meeting | Tech Lead and relevant members | Review architecture, implementation and integration | At least weekly | Meeting, diagram and pull request |
| Requirement review | Leader, BA, Tester and UI/UX | Review requirements, acceptance criteria and user flows | Per requirement milestone | Google Docs and meeting |
| AI-DLC approval review | Team and supervisor when required | Approve artifacts and open the next stage | At each formal checkpoint | Google Drive and meeting |
| Supervisor progress review | Supervisor and Leader | Validate scope, progress and milestone quality | Every two weeks | Report and demonstration |
| Pull-request review | Tech Lead and relevant reviewer | Review code, tests and compatibility | Per pull request | GitHub |
| Defect triage | Tech Lead, Tester and relevant owner | Prioritize defects and assign corrective work | Weekly during implementation | GitHub Issues |
| Iteration demonstration | Team and supervisor | Demonstrate completed functions and collect feedback | End of Weeks 7, 9 and 11 | Live demonstration |
| Release-readiness review | All members | Verify tests, deployment and fallback procedures | Week 13 | Checklist and meeting |
| Defense rehearsal | All members | Practice presentation and system demonstration | Weeks 14-15 | On-site or online rehearsal |

Important decisions, approval results and scope changes must be recorded in the relevant document, project issue or AI-DLC audit record.

## 6. Configuration Management

### 6.1 Document Management

Project documents are maintained in organizational Google Drive and in the repository’s aidlc-docs directory.

Formal reports follow this naming convention:

Report-[Number]_[Document Name]_v[Major.Minor]

The document-management process is:

1. The document owner creates or updates the document. 2. Another member reviews its content and consistency. 3. The Leader checks scope, schedule and report completeness. 4. The Tech Lead reviews technical content. 5. The BA verifies requirement consistency and traceability. 6. The Tester reviews test-related content. 7. The supervisor reviews formal milestones when required. 8. Approved documents receive a version and change-log entry. 9. Superseded versions are retained for traceability. 10. AI-DLC state and audit files are updated at the appropriate checkpoint.

Major versions represent approved milestones. Minor versions represent reviewed corrections that do not change the approved baseline.

### 6.2 Source Code Management

Source code is managed using Git and GitHub.

The repository structure includes:

- frontend for the Next.js application.

- backend for the Spring Boot modular monolith.

- worker for background-job processing.

- contracts for OpenAPI and job/event schemas.

- infra for Docker and deployment configuration.

- aidlc-docs for AI-DLC documentation.

The source-code process is:

1. Create an issue or approved work item. 2. Create a short-lived development branch. 3. Implement code and automated tests. 4. Commit changes using meaningful messages. 5. Open a pull request. 6. Run formatting, build and test checks. 7. Obtain review from the Tech Lead or assigned reviewer. 8. Resolve review comments and failed checks. 9. Merge only after all mandatory checks pass. 10. Tag approved software-package versions.

The main branch must remain deployable. Direct unreviewed changes to the main branch are not permitted.

Database migrations and public-contract changes require compatibility review. Secrets, passwords, API keys and private credentials must not be committed.

### 6.3 Tools and Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Frontend | Next.js and TypeScript |
| Backend | Java and Spring Boot modular monolith |
| Background Processing | Independent worker application |
| Database | PostgreSQL |
| Temporary State and Cache | Redis |
| Messaging | RabbitMQ |
| File Storage | Organizational Google Shared Drive |
| AI Integration | Provider-neutral AI/LLM adapter |
| Payment | Payment gateway adapter with verified webhooks |
| Notifications | Email and notification provider |
| Code Execution | Isolated Code Sandbox |
| Containerization | Docker and Docker Compose |
| API Contracts | OpenAPI |
| Job and Event Contracts | Versioned JSON schemas |
| IDEs and Editors | Visual Studio Code, IntelliJ IDEA or equivalent |
| Diagramming | Draw.io and Mermaid |
| UI/UX Design | Figma or equivalent prototyping tool |
| Documentation | Microsoft Word, Google Docs, Google Sheets, Google Slides and aidlc-docs |
| Version Control | Git and GitHub |
| Project Management | GitHub Projects or Issues, Google Drive and weekly WBS tracking |
| Testing | JUnit, Spring Boot Test, frontend testing tools and end-to-end testing tools |
| Continuous Integration | GitHub Actions or an equivalent CI pipeline |
| Deployment Environment | Docker-based staging environment |
| Monitoring | Structured logs, health checks and application metrics |